# BAT Corporate Campaign Planning Framework

SYNTHETIC knowledge source 1 of 4 | Primary framework

How the fictional 'Shape What's Next' employer-brand campaign is planned, governed and measured across six markets.

SYNTHETIC CIE TRAINING MATERIAL - Not official BAT information, policy, employee data, process, or findings.

## Document control

| Field | Value |
| --- | --- |
| Document | BAT Corporate Campaign Planning Framework (SYNTHETIC) |
| Document owner | Nadia Rahman (fictional), Head of Employer Brand - Synthetic |
| Version | v0.9 Draft for CIE |
| Status | Draft - approved for CIE training use only |
| Review date | 30 November 2026 |
| Applies to | Fictional employer-brand campaign 'Shape What's Next' (campaign code EB27) - adult audiences 21+ only |
| Related sources | Campaign Planning Framework ¦ Content and Localization Playbook ¦ Brand Claims and Approval Guide ¦ Campaign FAQ |
| Classification | SYNTHETIC CIE TRAINING MATERIAL - fictional owner, roles and contacts (.example domains) |

# 1. Purpose

This framework sets out how BAT marketing teams plan corporate and employer-brand campaigns, using the fictional 'Shape What's Next' graduate and early-careers campaign (code EB27) as the worked example. It covers research, briefing, content, localization, approval and measurement. It does NOT cover consumer product marketing of any kind; product marketing is out of scope and must never be mixed into employer-brand content.

# 2. Scope

Campaign type: corporate / employer-brand only - graduate programme, early careers, sustainability careers, women in engineering.

Audience: adults aged 21+ only: graduates (21+), early-career professionals, experienced STEM professionals and university careers advisers. No content may target or feature anyone under 21.

Markets: United Kingdom, France, Brazil, Egypt, UAE, Morocco.

Channels: Professional Network, Short-form Video, Photo Social, Careers Site, Campus Events, Email Newsletter.

Out of scope: consumer product promotion, retail activity, trade marketing, paid-media budget setting (Campaign Owner decision).

## 2.1 Market overview

| Market | Languages | Launch (applications open) | Local Market Comms Lead | Status |
| --- | --- | --- | --- | --- |
| United Kingdom | English | 1 February 2027 | UK Comms Lead (role) | Confirmed |
| France | French (FR-FR) | 1 February 2027 | France Comms Lead (role) | Confirmed |
| Brazil | Portuguese (PT-BR) | 1 February 2027 | Brazil Comms Lead (role) | Confirmed |
| Egypt | Arabic, English | 1 February 2027 | Egypt Comms Lead (role) | Confirmed |
| UAE | Arabic, English | 1 February 2027 | UAE Comms Lead (role) | Confirmed |
| Morocco | French (FR-MA), Arabic | To be confirmed by local team - not in this framework | To be confirmed by local team | Open |

INFORMATION GAP - Morocco launch date, local approver and French/Arabic language split are not defined in this framework. Do not assume 1 February 2027. Route to the Local Market Comms Lead via campaign-ops@bat-cie.example.

# 3. Campaign objectives and measures

| Objective | Measure (from campaign reporting) | Target |
| --- | --- | --- |
| Raise awareness of the graduate programme among adult graduates | Reach and engagement rate vs channel benchmark | Set per market by Campaign Owner |
| Drive qualified application starts | Careers Site visits -> application starts | Set per market by Campaign Owner |
| Broaden the applicant pool (incl. women in engineering) | Share of applications for engineering roles | Not in this framework - Talent Acquisition |
| Position sustainability careers credibly | Engagement on sustainability content (qualitative messages only) | No numeric claims permitted |

Numeric targets and paid-media budgets are human decisions by the Campaign Owner and are deliberately not included in this framework.

# 4. Roles and responsibilities

| Role (fictional) | Responsibility | Decision rights |
| --- | --- | --- |
| Campaign Owner | Overall plan, budget, market priority, go-live | Approves budget and go-live after Gates 1-3 |
| Employer Brand Lead | Brief quality, message strategy, Gate 1 | Signs off brief (Gate 1); resolves conflicting guidance |
| Content & Localization Manager | Content production, glossary, localization workflow | Assigns native reviewers; cannot approve claims |
| Brand Claims Reviewer | Checks every line against approved messages | Gate 2 claims decision |
| Marketing Legal | Product adjacency, audience age, new claims, legal risk | Can stop any asset; joins Gate 2 when flagged |
| Native-speaker Reviewer | Meaning, tone, culture, inclusive language | Gate 3 language check (with Local Comms Lead) |
| Local Market Comms Lead | Local fit, local rules, market launch | Gate 3 sign-off for their market |
| Privacy & Consent Review | Event registration data, employee images/testimonials | Consent decision |

# 5. Planning process

| Stage | What happens | Timing before launch | Output |
| --- | --- | --- | --- |
| 1 Research & insight | Analyse trend and engagement benchmarks; note sample sizes and evidence status | Week -10 to -8 | Insight summary |
| 2 Brief | Complete brief template (section 6) | Week -8 | Brief -> Gate 1 |
| 3 Concepts | 3 concepts per market from approved messages | Week -7 | Concept board |
| 4 Content production | Social posts, video scripts, articles, presentation | Week -6 to -4 | Draft assets -> Gate 2 |
| 5 Localization | Machine draft + native review + local sign-off | Week -4 to -2 | Localized assets -> Gate 3 |
| 6 Approval & scheduling | Approval Log complete; Campaign Owner go-live | Week -1 | Go-live decision |
| 7 Measure | Report vs benchmark; lessons learned | Launch +4 weeks | Performance note |

# 6. Campaign brief template

1. Objective

2. Audience (adults 21+ only - state segment)

3. Key insight (figure + sample size + evidence status)

4. Core message (approved messages AM-01 to AM-08 only, cite AM number)

5. Channels and formats

6. Localization needs (languages, native reviewers)

7. Approvals required (Gates 1-3)

8. Open questions / items to verify

# 7. Research and evidence rules

Use rows with Evidence_Source_Status = "Verified (synthetic panel)" for headline insights.

"Third-party estimate - unverified" and "Pending local validation" may inform hypotheses only and must be labelled as such.

Engagement benchmarks based on fewer than 20 benchmark posts are indicative only.

Trend data is evidence for planning - it is never an approved claim. A high search-interest theme still needs approved wording.

Always state counts, percentages and sample sizes when presenting research.

# 8. Controls and exceptions

No asset goes live without all three gates recorded in the Approval Log (see Brand Claims and Approval Guide, section 5).

Exceptions (e.g. shortened lead times) can only be granted by the Campaign Owner together with Marketing Legal; they are never self-approved.

Any product reference, product imagery or product-adjacent setting stops the asset immediately and goes to Marketing Legal.

Paid targeting must be set to 21+ in every market, even where local law allows a lower age.

# 9. Governance

The Employer Brand Lead reviews this framework quarterly. Conflicts between this framework and other campaign documents are resolved by the Employer Brand Lead; until resolved, the stricter rule applies.

## Boundaries for the Campaign Enablement agent

May explain the process, stages, roles, brief template and evidence rules in this framework.

Must not set targets, budgets, market priority or go-live dates; must not confirm Morocco details.

Must route conflicting guidance to the Employer Brand Lead (employer-brand@bat-cie.example).