# BAT TM&D Manager Playbook

How a Trade Manager TM&D runs the quarterly review cycle

Role playbook | Routines, checklists and decision boundaries | SYNTHETIC

SYNTHETIC CIE TRAINING MATERIAL - Not official BAT information, policy, employee data, process, or findings.

## Document control

| Field | Value |
| --- | --- |
| Document | BAT TM&D Manager Playbook |
| Owner (fictional) | Marco Ilescu (fictional), TM&D Capability Manager, Region Meridian |
| Version | v0.9 Draft for CIE |
| Status | Draft - synthetic, for CIE training only |
| Effective for | Q3 2026 Trade Business Review cycle, Region Meridian (fictional) |
| Review date | 30 November 2026 |
| Contact | tmd-review@bat-cie.example |
| Document set | Trade Business Review Framework; TM&D Manager Playbook; Commercial Decision and Escalation Guide; Business Review FAQ (all synthetic) |

# 1. Who this is for

Trade Managers TM&D who prepare and present market performance in the quarterly Trade Business Review (TBR). It turns the Trade Business Review Framework into week-by-week routines and shows where Copilot can save time and where a human must decide.

# 2. The review cycle at a glance

| When | What you do | Where Copilot helps | Human checkpoint |
| --- | --- | --- | --- |
| BD1-BD5 (before data lock) | Close last quarter's actions; confirm data feeds with distributors | Summarise open actions from the tracker | Raise data gaps to TM&D Insights Team |
| BD5-BD8 (analysis) | RAG by market-channel; root cause for every Red; customer insights | Excel: summaries, variance, top/bottom accounts, charts | Check every figure against the source file |
| BD8-BD10 (brief) | Write the 2-page executive brief | Word: draft brief in the six-section structure | You own the wording and the options |
| BD10-BD12 (pack) | Build the review section and pre-read | PowerPoint: deck from brief; Teams: pre-read message | Pre-read sent 48 hours before |
| Review day (60 min) | Present, request decisions, agree actions | Teams: meeting recap and action list | Decisions recorded by the chair |
| BD+2 and weekly | Update tracker; weekly 30-minute TM&D huddle (Mondays) | Teams: follow-up drafts; agent: escalation routes | Escalate overdue > 14 days |

# 3. Routines

Weekly huddle (Mondays, 30 min): review overdue and not-started actions by market; confirm owner roles; flag decisions needing escalation.

Monthly customer insight review: top five accounts by negative gap vs plan, distribution changes, competitive signals.

Quarterly TBR: follow the Framework stages 1-6; maximum two deep-dives.

After every customer interaction: log commitments requested by the customer as actions with decision topic 'Customer terms' - never agree terms in the meeting.

# 4. Checklists

## 4.1 Executive brief checklist

☐ Six sections present, maximum 2 pages

☐ Every percentage has a sample size

☐ Red items have root cause, recovery plan, owner and due date

☐ Evidence and inference visibly separated

☐ Decisions requested are framed as options with owner and route - not as decisions taken

☐ Labelled DRAFT until reviewed; synthetic label kept in training

## 4.2 Meeting preparation checklist

☐ Pre-read sent 48 hours before

☐ Agenda follows the 60-minute standard

☐ Three likely leadership questions prepared with evidence

☐ Overdue actions list with days overdue

☐ Decision requests pre-routed per Escalation Guide

☐ Local market items needing confirmation flagged

## 4.3 Action follow-up checklist

☐ Tracker updated within 2 business days

☐ Each action: one owner role, due date, decision topic

☐ Follow-up message drafted, reviewed, then sent by you

☐ Overdue > 14 days escalated to Regional TM&D Lead

# 5. Using Copilot well in TM&D work

Name the source file, sheet and columns in the prompt (e.g. Value_Var_pct in Trade_Data).

Ask for counts, percentages and sample sizes; ask Copilot to separate evidence from inference.

Tell Copilot not to invent figures, policy or local rules, and to flag market-specific limitations.

Review every number against the workbook before sharing; Copilot can be wrong.

# 6. Human decision boundaries

| Decision | TM&D manager may | Must not (route instead) |
| --- | --- | --- |
| Pricing | Describe competitive signals and evidence | Decide or recommend a price response -> Regional RGM Lead + Market GM |
| Customer terms | Listen, log the request, prepare a neutral note | Agree terms, discounts, listing or display payments -> Customer Commercial Council |
| Trade investment | Approve up to EUR 50k only if they are the Market Head of Trade Marketing | Approve above EUR 50k -> Regional TM&D Lead / Regional Commercial Committee |
| Portfolio | Present range performance | Decide listing/delisting -> Regional Portfolio Committee |
| People | Assign action owner roles | Judge individual performance -> line manager + HR Business Partner |

# 7. New to the role? First four weeks

| Week | Focus |
| --- | --- |
| 1 | Read the Framework, this Playbook and the Escalation Guide; shadow a weekly huddle. |
| 2 | Walk through the last TBR pack and action tracker with the Regional TM&D Lead. |
| 3 | Prepare a practice executive brief from the current performance file; get feedback. |
| 4 | Run the weekly huddle for one market; route one decision request end to end. |

# 8. Local items not covered

Türkiye local promotion spend ceiling and approval route: To be confirmed by local team - not in this framework.

Romania Traditional Trade route-to-market (distributor change) approval route: To be confirmed by Romania market leadership - not in this framework.